## Overall status
| Backplane |  | DCB |  | LVR |  |  | P2B2 | Opt. Mezz. | CCM
| Ordered | 30 | Ordered | 270 | Ordered | 295 | Ordered | 30 | 1080 | 1958
The received row is to be filled manually | Received | 30 | Received | 270 | Received | 295 | Received | 30 | 1080 | 1958
| Burned-in | 24 | Assembled | 50 | Set up/QA | 39 | QA | 6 | 124 | 799
| Initial QA | 9 | Set up/QA | 31 | Assembled | 39
| Assembled | 6 | Burned-in | 0 | Burned-in | 5
| Final QA | 6 | Final QA | 0 | Final QA | 0

## Backplane
Backplanes (+ P2B2s)
Status Summary
Type-Variant | Burned-in | QA'ed
True-F | 4 | 1
True-P | 5 | 1
True-D | 3 | 1
Mirror-F | 3 | 1
Mirror-D | 6 | 1
Mirror-P | 3 | 1
Total | 24 | 6
Type | Variant | SN | ID (Type+Variant+unique#) | Location | Visual Inspection | Burn-in | QA | Assembly | Notes
True | F | 002-001 | TF1 | CERN | Yes | Yes | Yes | Yes | Have re-done continuity test with new P2B2
True | F | 002-002 |  | UMD | Yes | No | Yes | No | RMA reworked. See https://github.com/umd-lhcb/lab-notes/issues/53#issuecomment-557333122
True | F |  |  |  | Yes | Yes
True | F |  |  |  | Yes | Yes
True | F |  |  |  | Yes | Yes
True | P | 016-002 | TP3 | CERN | Yes | Yes | Yes | Yes | Depopulation to be verified
True | P |  |  |  | Yes | Yes
True | P |  |  |  | Yes | Yes
True | P |  |  |  | Yes | Yes
True | P |  |  |  | Yes | Yes
True | P
True | P
True | D | 012-001 | TD5 | CERN | Yes | Yes | Yes | Yes | Depopulation to be verified
True | D |  |  |  | Yes | Yes
True | D |  |  |  | Yes | Yes
Mirror | F | 001-001 |  | UMD | Yes | Yes | Yes | No | * Being used in PEPI crate stave testing -- considered burned-in.
Mirror | F | 004-002 |  | UMD | Yes | No | Yes | No | RMA reworked. See https://github.com/umd-lhcb/lab-notes/issues/57#issuecomment-573737356
Mirror | F | 006-002 | MF2 | CERN | Yes | Yes | Yes | Yes
Mirror | F |  |  |  | Yes | Yes
Mirror | F
Mirror | P | 013-002 | MP4 | CERN | Yes | Yes | Yes | Yes | Depopulation to be verified
Mirror | P |  |  |  | Yes | Yes
Mirror | P |  |  |  | Yes | Yes
Mirror | P |  |  |  | Yes | Yes
Mirror | P |  |  |  | Yes | Yes
Mirror | P |  |  |  | Yes | Yes
Mirror | P
Mirror | D | 012-001 |  | UMD | Yes | Yes |  |  | To be RMAed: https://github.com/umd-lhcb/lab-notes/issues/53#issuecomment-592755581
Mirror | D | 008-001 |  | UMD | Yes | Yes |  |  | To be RMAed: https://github.com/umd-lhcb/lab-notes/issues/53#issuecomment-592755581
Mirror | D | 008-002 | MD6 | CERN | Yes | Yes | Yes | Yes | Depopulation to be verified

## DCB
DCBs (Data Control Boards)
|  |  |  | Initial QA |  |  |  |  | Final QA
| ID | Location | Assembled | Fused | PRBS good | 1.5V current [A] | 2.5V current [A] | Burned in | Stave Test Slot JD10 | Stave Test Slot JD11 | Comments
A1
A2
| A3 | SYR | Yes | Yes
A4
| A5 | UMD | [8 empty] | BAD
| A6 | UMD |  | Yes
A7
A8
| A9 | SYR | yes | Yes | yes | yes | yes |  | yes | yes | Did not check ADC 2 during initial QA
| A10 | UMD
| A11 | SYR | Yes | Yes
| A12 | UMD |  | Yes | [6 empty] | fused with new master configuration file
| A13 | UMD |  | Prob | [6 empty] | Fuse problem
| A14 | UMD |  | Yes
WVJCE-001 | 1 | UMD | Yes | yes | yes
WVJCE-002 | 2 | UMD | Yes | yes | yes
WVJCE-003 | 3 | UMD | Yes | yes | yes
WVJCE-004 | 4 | UMD | Yes | yes | yes | [5 empty] | TP5 to backplate had resistance of 1-2 ohms, due to extra globs of solder on back, fixed with capton tape. | resolved
WVJCE-005 | 5 | UMD | Yes | yes | yes
WVJCE-006 | 6 | UMD | Yes | yes | yes
WVJCE-007 | 7 | UMD | Disassembled | yes | [6 empty] | TP5 to backplate res < 1ohm, caused power to shut off when fusing; Took apart applied more thermal paste then reassembled, found a scratch on the back of the DCB and a bent pin on the master optical mezzanine slot; Succeeded in fusing board. Returning to manufacturer to fix bent pin (J7, pin 58)
WVJCE-008 | 8 | UMD | Yes | yes | yes
WVJCE-009 | 9 | UMD | Yes | yes | yes
WVJCE-010 | 10 | UMD | Yes | yes | yes
WVJCE-011 | 11 | UMD | Yes | yes | yes | [5 empty] | fused twice
WVJCE-012 | 12 | UMD | Yes | yes | yes
WVJCE-013 | 13 | UMD | Yes | yes | yes | [5 empty] | GBTx not being detected after writing master txt, not going to waitDESlLock, alternating between different statuses -> goes away when 2v5 powered
WVJCE-014 | 14 | UMD | Yes | yes | yes
WVJCE-015 | 15 | UMD | Yes | yes | yes | 4.55 | 0.78
WVJCE-016 | 16 | UMD | yes | yes | yes | [5 empty] | MC Mezzanine difficult to install, need to go on new backplate
WVJCE-017 | 17 | UMD | yes | yes | yes
WVJCE-018 | 18 | UMD | Yes | yes | yes | [5 empty] | After writing GBTx not going to waitDESLock, alternating statuses -> goes away when 2v5 powered
WVJCE-019 | 19 | UMD | Yes | yes | yes
WVJCE-020 | 20 | UMD | Yes | yes | yes
WVJCE-021 | 21 | UMD | Yes | yes
WVJCE-022 | 22 | UMD | yes | yes | yes | [5 empty] | careful when handling, lots of thermal paste
WVJCE-023 | 23 | UMD | Yes | yes | yes
WVJCE-024 | 24 | UMD | Yes | yes | yes | [5 empty] | goes to idle after writing master.txt when 2v5 is not powered. Otherwise, locks normally.
WVJCE-025 | 25 | UMD | Yes | yes | yes | 4.56 | 0.78
WVJCE-026 | 26 | UMD | Yes | yes | bad | [5 empty] | GBTx #3 reports errors instantly, test pattern and memory monitoring looks good
WVJCE-027 | 27 | UMD | yes | yes | yes
WVJCE-028 | 28 | UMD | Yes | yes | yes
WVJCE-029 | 29 | UMD | yes | [7 empty] | problem with fusing, the computer does not recognize the board as connected
WVJCE-030 | 30 | UMD | yes | yes | yes | 4.65 | 0.78
WVJCE-031 | 31 | UMD | yes | yes | yes | 4.55 | 0.78 |  |  |  | Originally had jumper J13 in wrong place (shorting the board) and was run with 3.3V, fixed jumper position and proceeded to fuse and complete PRBS without problem
WVJCE-032 | 32 | UMD | yes | yes | [6 empty] | invalid input sequence for GBT 2,3/ saw data valid not being pulled up
WVJCE-033 | 33 | UMD | yes | yes | yes
WVJCE-034 | 34 | UMD | yes | yes | yes | 4.58 | 0.79
WVJCE-035 | 35 | UMD | yes | yes | yes | 4.64 | 0.8
WVJCE-036 | 36 | UMD | yes
WVJCE-037 | 37 | UMD | yes
WVJCE-038 | 38 | UMD | yes
WVJCE-039 | 39 | UMD | yes | yes | yes | 4.57 | 0.77
WVJCE-040 | 40 | UMD | yes
WVJCE-041 | 41 | UMD | Yes
WVJCE-042 | 42 | UMD | yes
WVJCE-043 | 43 | UMD | yes
WVJCE-044 | 44 | UMD | Yes
WVJCE-045 | 45 | UMD | Yes
WVJCE-046 | 46 | UMD | Yes
WVJCE-047 | 47 | UMD | Yes
WVJCE-048 | 48 | UMD | Yes | [7 empty] | problem with fusing, the computer does not recognize the board as connected
WVJCE-049 | 49 | UMD | Yes
WVJCE-050 | 50 | UMD | Yes
WVJCE-051 | 51 | UMD | Yes
WVJCE-052 | 52 | UMD | [8 empty] | backplate
WVJCE-053 | 53 | UMD
WVJCE-054 | 54 | UMD
WVJCE-055 | 55 | UMD
WVJCE-056 | 56 | UMD
WVJCE-057 | 57 | UMD
WVJCE-058 | 58 | UMD
WVJCE-059 | 59 | UMD
WVJCE-060 | 60 | UMD
WVJCE-061 | 61 | UMD
WVJCE-062 | 62 | UMD
WVJCE-063 | 63 | UMD
WVJCE-064 | 64 | UMD
WVJCE-065 | 65 | UMD
WVJCE-066 | 66 | UMD
WVJCE-067 | 67 | UMD
WVJCE-068 | 68 | UMD
WVJCE-069 | 69 | UMD
WVJCE-070 | 70 | UMD
WVJCE-071 | 71 | UMD
WVJCE-072 | 72 | UMD
WVJCE-073 | 73 | UMD
WVJCE-074 | 74 | UMD
WVJCE-075 | 75 | UMD
WVJCE-076 | 76 | UMD
WVJCE-077 | 77 | UMD
WVJCE-078 | 78 | UMD
WVJCE-079 | 79 | UMD
WVJCE-080 | 80 | UMD
WVJCE-081 | 81 | UMD
WVJCE-082 | 82 | UMD
WVJCE-083 | 83 | UMD
WVJCE-084 | 84 | UMD
WVJCE-085 | 85 | UMD
WVJCE-086 | 86 | UMD
WVJCE-087 | 87 | UMD
WVJCE-088 | 88 | UMD
WVJCE-089 | 89 | UMD
WVJCE-090 | 90 | UMD
WVJCE-091 | 91 | UMD
WVJCE-092 | 92 | UMD
WVJCE-093 | 93 | UMD
WVJCE-094 | 94 | UMD
WVJCE-095 | 95 | UMD
WVJCE-096 | 96 | UMD
WVJCE-097 | 97 | UMD
WVJCE-098 | 98 | UMD
WVJCE-099 | 99 | UMD
WVJCE-100 | 100 | UMD
WVJCE-101 | 101 | UMD
WVJCE-102 | 102 | UMD
WVJCE-103 | 103 | UMD
WVJCE-104 | 104 | UMD
WVJCE-105 | 105 | UMD
WVJCE-106 | 106 | UMD
WVJCE-107 | 107 | UMD
WVJCE-108 | 108 | UMD
WVJCE-109 | 109 | UMD
WVJCE-110 | 110 | UMD
WVJCE-111 | 111 | UMD
WVJCE-112 | 112 | UMD
WVJCE-113 | 113 | UMD
WVJCE-114 | 114 | UMD
WVJCE-115 | 115 | UMD
WVJCE-116 | 116 | UMD
WVJCE-117 | 117 | UMD
WVJCE-118 | 118 | UMD
WVJCE-119 | 119 | UMD
WVJCE-120 | 120 | UMD
WVJCE-121 | 121 | UMD
WVJCE-122 | 122 | UMD
WVJCE-123 | 123 | UMD
WVJCE-124 | 124 | UMD
WVJCE-125 | 125 | UMD
WVJCE-126 | 126 | UMD
WVJCE-127 | 127 | UMD
WVJCE-128 | 128 | UMD
WVJCE-129 | 129 | UMD
WVJCE-130 | 130 | UMD
WVJCE-131 | 131 | UMD
WVJCE-132 | 132 | UMD
WVJCE-133 | 133 | UMD
WVJCE-134 | 134 | UMD
WVJCE-135 | 135 | UMD
WVJCE-136 | 136 | UMD
WVJCE-137 | 137 | UMD
WVJCE-138 | 138 | UMD
WVJCE-139 | 139 | UMD
WVJCE-140 | 140 | UMD
WVJCE-141 | 141 | UMD
WVJCE-142 | 142 | UMD
WVJCE-143 | 143 | UMD
WVJCE-144 | 144 | UMD
WVJCE-145 | 145 | UMD
WVJCE-146 | 146 | UMD
WVJCE-147 | 147 | UMD
WVJCE-148 | 148 | UMD
WVJCE-149 | 149 | UMD
WVJCE-150 | 150 | UMD
WVJCE-151 | 151 | UMD
WVJCE-152 | 152 | UMD
WVJCE-153 | 153 | UMD
WVJCE-154 | 154 | UMD
WVJCE-155 | 155 | UMD
WVJCE-156 | 156 | UMD
WVJCE-157 | 157 | UMD
WVJCE-158 | 158 | UMD
WVJCE-159 | 159 | UMD
WVJCE-160 | 160 | UMD
WVJCE-161 | 161 | UMD
WVJCE-162 | 162 | UMD
WVJCE-163 | 163 | UMD
WVJCE-164 | 164 | UMD
WVJCE-165 | 165 | UMD
WVJCE-166 | 166 | UMD
WVJCE-167 | 167 | UMD
WVJCE-168 | 168 | UMD
WVJCE-169 | 169 | UMD
WVJCE-170 | 170 | UMD

## LVR
LVRs (Low Voltage Regulators)
[9 empty] | Initial QA | [10 empty] | Burn-In
|  |  |  | ID | Location | Serial - LVR | Serial - CCMs (Note QTY) | LVR Type (12MS, 12A, 12MSA, 15MS, 25A) | 1v5, 3v3, and Op Rail | FPGA Programmed? | Undervolt + overtemp configged? | Undervolt test | Overtemp Test | Output standby configuration | Sense line test | SPI Test | QA OK | Assembled | in SBC crate? | Start time | End time | Final QA | Subtype | Comments
Summary |  |  |  | A1
Type | Subtype | System | Have | A2
12A | 8ch, FF | 48 | 0 | A3
12A | 7ch, FE | 16 | 0 | A4
12A | 7ch, FD | 16 | 0 | A5 | UMD | [18 empty] | BAD
12A | 6ch, FA | 24 | 0 | A6 | UMD |  | Yes
12A | 6ch, DD | 8 | 0 | A7
12A | 5ch, D9 | 8 | 0 | A8
12A | 4ch, F0 | 8 | 0 | A9 | UMD |  | Yes
12MSA | 5ch, F8 | 16 | 0 | A10 | UMD
12MS | 8ch, FF | 32 | 0 | A11
15MS | 8ch, FF | 56 | 0 | A12 | UMD
15MS | 4ch, 33 | 12 | 0 | A13 | UMD |  | Prob | [16 empty] | Fuse problem
25A | 6ch, 6F | 8 | 0 | A14 | UMD |  | Yes
25A | 5ch, 4F | 12 | 0 | 1 | UMD | WVJCZ-001 | 12A5 | 12A | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | TRUE | Yes | Yes |  |  |  |  | Good
25A | 4ch, 0F | 4 | 0 | 2 | UMD | WVJCZ-002 | 25A09 | 25A | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | TRUE | Yes | Yes | 3:00:00 PM 03/10 | 1:30:00 PM 03/12 |  |  | bent monitor pins on upper two left. Also current of CCM's decreased on both sides of the board (for ex. ch 1 had ~0.75 A while ch 4 had ~0.51 A)
TOTALS |  |  |  | 3 | UMD | WVJCZ-003 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes | Yes
Type | Need | initial QA | final | 4 | UMD | WVJCZ-004 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes | Yes | 3:00:00 PM 03/10 | 1:30:00 PM 03/12
12A | 128 | 16 | 0 | 5 | UMD | WVJCZ-005 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes | [5 empty] | *Resolved* CCM current decrease on channels 1-4 from ~0.75A to ~0.54A
12MSA | 16 | 0 | 0 | 6 | UMD | WVJCZ-006 | 15M5/15S5 | 15MS | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | TRUE | yes
12MS | 32 | 0 | 0 | 7 | UMD | WVJCZ-007 | 15M5/15S5 | 15MS | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | TRUE | yes
15MS | 68 | 12 | 0 | 8 | UMD | WVJCZ-008 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes | Yes
25A | 24 | 11 | 0 | 9 | UMD | WVJCZ-009 | 12A5 | 12A | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | TRUE | Yes | Yes | 3:00:00 PM 04/10 | 1:30:00 PM 03/12 |  |  | Good
LVR | 268 | 39 | 0 | 10 | UMD | WVJCZ-010 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes | Yes
|  |  |  | 11 | UMD | WVJEN-011 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes | [5 empty] | 0
|  |  |  | 12 | UMD | WVJEN-012 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes | Yes
|  |  |  | 13 | UMD | WVJEN-013 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes
|  |  |  | 14 | UMD | WVJEN-014 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes | Yes
|  |  |  | 15 | UMD | WVJEN-002 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes | Yes |  |  |  |  | Could only adjust Opamp Rail to 5.481 V
|  |  |  | 16 | UMD | WVJEN-003 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes | Yes
|  |  |  | 17 | UMD | WVJEN-006 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes
|  |  |  | 18 | UMD | WVJEN-001 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes | Yes | 3:00:00 PM 03/10 | 1:30:00 PM 03/12
|  |  |  | 19 | UMD | WVJEN-010 | 15M5/15S5 | 15MS | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes | Yes | 3:00:00 PM 03/10 | 1:30:00 PM 03/12
|  |  |  | 20 | UMD | WVJEN-004 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes
|  |  |  | 21 | UMD | WVJEN-018 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes | Yes
|  |  |  | 22 | UMD | WVJEN-005 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes
|  |  |  | 23 | UMD | WVJEN-020 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes
|  |  |  | 24 | UMD | WVJEN-009 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes | Yes
|  |  |  | 25 | UMD | WVJEN-007 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes
|  |  |  | 26 | UMD | WVJEN-008 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | Yes
|  |  |  | 27 | UMD | WVJER-002 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes | TRUE | yes
|  |  |  | 28 | UMD | WVJER-001 | 12A5 | 12A | No | [14 empty] | P5 had broken lead going to pad. Cannot be tuned - needs to be resoldered/sent back. Will is sending a message to the manufacturer to see if this might be indicative of a systemic issue on the board.
|  |  |  | 29 | UMD | WVJER-018 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | Yes | Yes
|  |  |  | 30 | UMD | WVJER-019 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
|  |  |  | 31 | UMD | WVJER-016 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | Yes
|  |  |  | 32 | UMD | WVJER-017 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes |  | Yes
|  |  |  | 33 | UMD | WVJER-014 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
|  |  |  | 34 | UMD | WVJER-012 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
|  |  |  | 35 | UMD | WVJER-013 | 25A09 | 25A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
|  |  |  | 36 | UMD | WVJER-010 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
|  |  |  | 37 | UMD | WVJER-011 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
|  |  |  | 38 | UMD | WVJES-012 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes | [5 empty] | Chassis resistance to board ground was about half of what it normally is - ~100 kOhms in both directions compared to a more typical 200 kOhms
|  |  |  | 39 | UMD | WVJER-015 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
|  |  |  | 40 | UMD | WVJES-011 | 12A5 | 12A | yes | yes | yes | yes | yes | yes | yes | yes |  | yes
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69

## LVR Subtypes
8ch, FF |  |  |  | 7ch, FE |  |  |  | 7ch, FD |  |  |  | 6ch, FA |  |  |  | 6ch, DD
| INPUT |  |  |  | INPUT |  |  |  | INPUT |  |  |  | INPUT |  |  |  | INPUT
5 | CCM | CCM | 4 | 5 | CCM | CCM | 4 | 5 | CCM | CCM | 4 | 5 | CCM | CCM | 4 | 5 | CCM | CCM | 4
6 | CCM | CCM | 3 | 6 | CCM | CCM | 3 | 6 | CCM | CCM | 3 | 6 | open | CCM | 3 | 6 | CCM | CCM | 3
7 | CCM | CCM | 2 | 7 | CCM | CCM | 2 | 7 | open | CCM | 2 | 7 | CCM | CCM | 2 | 7 | open | open | 2
8 | CCM | CCM | 1 | 8 | open | CCM | 1 | 8 | CCM | CCM | 1 | 8 | open | CCM | 1 | 8 | CCM | CCM | 1
OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT
5ch, D9 |  |  |  | 4ch, F0 |  |  |  | 5ch, F8 |  |  |  | 4ch, 33 |  |  |  | 6ch, 6F
| INPUT |  |  |  | INPUT |  |  |  | INPUT |  |  |  | INPUT |  |  |  | INPUT
5 | CCM | CCM | 4 | 5 | open | CCM | 4 | 5 | CCM | CCM | 4 | 5 | CCM | CCM | 4 | 5 | CCM | open | 4
6 | CCM | open | 3 | 6 | open | CCM | 3 | 6 | open | CCM | 3 | 6 | CCM | CCM | 3 | 6 | CCM | CCM | 3
7 | open | open | 2 | 7 | open | CCM | 2 | 7 | open | CCM | 2 | 7 | open | open | 2 | 7 | CCM | CCM | 2
8 | CCM | CCM | 1 | 8 | open | CCM | 1 | 8 | open | CCM | 1 | 8 | open | open | 1 | 8 | CCM | open | 1
OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT
5ch, 4F |  |  |  | 4ch, 0F
| INPUT |  |  |  | INPUT
5 | CCM | open | 4 | 5 | CCM | open | 4
6 | CCM | CCM | 3 | 6 | CCM | open | 3
7 | CCM | open | 2 | 7 | CCM | open | 2
8 | CCM | open | 1 | 8 | CCM | open | 1
OUTPUT |  | OUTPUT |  | OUTPUT |  | OUTPUT

## CCM
| 12A | 12M | 12S | 15M | 15S | 25A
MFG's Packing list Totals
| 933 | 176 | 176 | 268 | 268 | 137
Total Tested
| 243 | 0 | 0 | 268 | 175 | 113
Total Good
| 239 | 0 | 0 | 268 | 175 | 113
Total in Storage (excluding CCMs taken out for use elsewhere)
| 193 | 0 | 0 | 240 | 135 | 89
Roll ID | Location | CCM Type | Master or Slave | Original # of CCMs in Roll | Good CCMs in Roll | CCMs being used (LVR QA, etc) | CCM Usage (what CCMs being used for) | Other comments
15M1 | UMD | 1.5 | Master | 12 | 12
15M2 | UMD | 1.5 | Master | 12 | 12
15M3 | UMD | 1.5 | Master | 12 | 12
15M4 | UMD | 1.5 | Master | 7 | 7
15M5 | UMD | 1.5 | Master | 12 | 12 | 4 | LVR QA
15M6 | UMD | 1.5 | Master | 12 | 12
15M7 | UMD | 1.5 | Master | 12 | 12
15M8 | UMD | 1.5 | Master | 12 | 12
15M9 | UMD | 1.5 | Master | 12 | 12
15M10 | UMD | 1.5 | Master | 12 | 12
15M11 | UMD | 1.5 | Master | 12 | 12
15M12 | UMD | 1.5 | Master | 12 | 12
15M13 | UMD | 1.5 | Master | 12 | 12
15M14 | UMD | 1.5 | Master | 12 | 12
15M15 | UMD | 1.5 | Master | 12 | 12
15M16 | UMD | 1.5 | Master | 9 | 9
15M17 | UMD | 1.5 | Master | 12 | 12
15M18 | UMD | 1.5 | Master | 12 | 12
15M19 | UMD | 1.5 | Master | 12 | 12
15M20 | UMD | 1.5 | Master | 12 | 12
15M21 | UMD | 1.5 | Master | 12 | 12 | 12 | LVR Burn-In
15M22 | UMD | 1.5 | Master | 12 | 12 | 12 | LVR Burn-In
15M23 | UMD | 1.5 | Master | 12 | 12
15S1 | UMD | 1.5 | Slave | 12 | 12
15S2 | UMD | 1.5 | Slave | 12 | 12
15S3 | UMD | 1.5 | Slave | 12 | 12
15S4 | UMD | 1.5 | Slave | 12 | 12
15S5 | UMD | 1.5 | Slave | 12 | 12 | 4 | LVR QA
15S6 | UMD | 1.5 | Slave | 12 | 12
15S7 | UMD | 1.5 | Slave | 12 | 12
15S8 | UMD | 1.5 | Slave | 12 | 12 | 12 | LVR Burn-In
15S9 | UMD | 1.5 | Slave | 7 | 7
15S10 | UMD | 1.5 | Slave | 12 | 12
15S11 | UMD | 1.5 | Slave | 12 | 12 | 12 | LVR Burn-In
15S12 | UMD | 1.5 | Slave | 12 | 12
15S13 | UMD | 1.5 | Slave | 12 | 12 | 12 | LVR Burn-In
15S14 | UMD | 1.5 | Slave | 12 | 12
15S15 | UMD | 1.5 | Slave | 12 | 12
15S16 | UMD | 1.5 | Slave
15S17 | UMD
15S18 | UMD
15S19 | UMD
15S20 | UMD
15S21 | UMD
15S22 | UMD
UMD
UMD
UMD
UMD
UMD
UMD
UMD
UMD
12A1 | UMD | 1.2 | Alone | 12 | 12
12A2 | UMD | 1.2 | Alone | 12 | 12
12A3 | UMD | 1.2 | Alone | 12 | 12 | 12 | LVR Burn-In
12A4 | UMD | 1.2 | Alone | 12 | 12 | 8 | Burn in testing
12A5 | UMD | 1.2 | Alone | 12 | 11 | 8 |  | As reported to Phoebe, 12A0049 has an odd Vbottom curve. 8 being used in LVR QA
12A6 | UMD | 1.2 | Alone | 20 | 18 | 18 | Burn in testing | 12A0061 and 12A0062 have the same outlier Vbottom curve as 12A0049.
12A7 | UMD | 1.2 | Alone | 12 | 12
12A8 | UMD | 1.2 | Alone | 12 | 12
12A9 | UMD | 1.2 | Alone | 12 | 12
12A10 | UMD | 1.2 | Alone | 12 | 12
12A11 | UMD | 1.2 | Alone | 12 | 12
12A12 | UMD | 1.2 | Alone | 6 | 6
12A13 | UMD | 1.2 | Alone | 12 | 12
12A14 | UMD | 1.2 | Alone | 12 | 12
12A15 | UMD | 1.2 | Alone | 12 | 12
12A16 | UMD | 1.2 | Alone | 12 | 11
12A17 | UMD | 1.2 | Alone | 12 | 12
12A18 | UMD | 1.2 | Alone | 12 | 12
12A19 | UMD | 1.2 | Alone | 13 | 13
12A20 | UMD | 1.2 | Alone | 12 | 12
12A21 | UMD
12A22 | UMD
12A23 | UMD
12A24 | UMD
12A25 | UMD
12A26 | UMD
12A27 | UMD
12A28 | UMD
12A29 | UMD
12A30 | UMD
12A31 | UMD
12A32 | UMD
12A33 | UMD
12A34 | UMD
12A35 | UMD
12A36 | UMD
12A37 | UMD
12A38 | UMD
12A39 | UMD
12A40 | UMD
12A41 | UMD
12A42 | UMD
12A43 | UMD
12A44 | UMD
12A45 | UMD
12A46 | UMD
12A47 | UMD
12A48 | UMD
12A49 | UMD
12A50 | UMD
12A51 | UMD
12A52 | UMD
12A53 | UMD
12A54 | UMD
12A55 | UMD
12A56 | UMD
12A57 | UMD
12A58 | UMD
12A59 | UMD
12A60 | UMD
12A61 | UMD
12A62 | UMD
12A63 | UMD
12A64 | UMD
12A65 | UMD
12A66 | UMD
12A67 | UMD
12A68 | UMD
12A69 | UMD
12A70 | UMD
12A71 | UMD
12A72 | UMD
12A73 | UMD
12A74 | UMD
12A75 | UMD
12A76 | UMD
12A77 | UMD
12A78 | UMD
12A79 | UMD
12A80 | UMD
25A01 | UMD | 2.5 | Alone | 9 | 9
25A02 | UMD | 2.5 | Alone | 12 | 12
25A03 | UMD | 2.5 | Alone | 12 | 12
25A04 | UMD | 2.5 | Alone | 9 | 9
25A05 | UMD | 2.5 | Alone | 12 | 12
25A06 | UMD | 2.5 | Alone | 12 | 12
25A07 | UMD | 2.5 | Alone | 12 | 12
25A08 | UMD | 2.5 | Alone | 12 | 12 | 12 | LVR Burn-In
25A09 | UMD | 2.5 | Alone | 11 | 11 | Serial #410-417 | LVR QA
25A10 | UMD | 2.5 | Alone | 12 | 12 | 12 | LVR Burn-In